## Working sheet 2014 (hidden)
Sustainable Land Management in Churia Region Nepal (GEF funded)
Year 1 (CY14) |  |  | Year 2 (CY15) |  | Year 3 (CY16) |  | Total
Budget | Expense | Spending % | Budget | Expense | Budget | Expense | Budget | Expenses | Spending %
381537.5 | 285038.04 | 74.71% | 301292.3733 | 0 | 234601.1987 | 0 | 917431.072 | 285038.04 | 31.07%
Savings from 2014
Exp Jun-Dec | 99253.17
Exp Jan-Jun | 210890.72
Total | 310143.89 | exp reported to HQ | grant and consultancy obligation
Savings | 71393.61 | 285038.04 | 25105.85 | 96499.46
2015 Budget | 397791.8333
Activities transferred to 2015 from 2014
2201 | Obligation Deductable - Grants
| WT47 |  |  |  |  | -10024 | -103.78
| WT81 |  |  |  |  | -388765.62 | -4042.69
| WT82 | [5 empty] | -0.97
| WT83 |  |  |  |  | -1781813 | -18359.25
| WU22 |  |  |  |  | -20800 | -218.99
| Total |  |  |  |  | -2201402.62 | -22725.68
2206/07 | Obligation Deductable - Consultancy
| WU62 |  |  |  |  | -150650 | -1529.91
| WV81 |  |  |  |  | -85000 | -850.26
| Total |  |  |  |  | -235650 | -2380.17
| Total of grants and consultancy | [5 empty] | -25105.85 | reconciled
Note on K9: Author: DSA, communication and monitoring visits; implementing visits For all 4 project sites and implementing partners

## Guidance
Guidance
Password: GEF (To unlock the sheet to insert new rows, copy over formulas, etc). The sheet was protected to prevent accidental error in the formulas of the sheet PURPOSE This template serves two functions: 1) Template for drafting the Annual Work Plan and Budget (AWP&B), based on the full project workplan. The purpose of the AWP&B is to ensure that activities planned for the project year will be successful at meeting the Results Framework targets, and are budgeted correctly. 2) Tracking progress against the Work Plan and Budget and the Results Framework (RF). Formulas are built into the AWP&B and Results Framework tabs to support tracking, and this is based on an average achievement of all activities/RF targets. Progress is rated annually in the Project Progress Report – the Implementation Progress Rating corresponds to AWP&B achievement, while the Development Objective Rating corresponds to achievement against the RF. One should not have over 100% achievement even if the target was exceeded.
Drafting the Annual Work Plan and Budget Output tracking (light orange row in AWP&B tab): Achievement of each output should be monitored over the lifetime of the project. If the activities underneath the output provide sufficient information on whether or not an output was achieved, no separate output target/indicator is required. Only include a target if the output is expected to be achieved for the given project year. Activities: Activities should be developed based on the ProDoc and what is needed to meet the Results Framework targets. Include relevant activities related to the Gender Action Plan and Stakeholder Engagement Plan. Please ensure alignment with the overall project workplan and ensure that the activities are relevant towards achieving the outputs. The outputs then should be relevant to achieving the results in the Results Framework. Targets/Units: Targets should always be numerical. The unit being measured should be included (e.g. # of meetings). Work plan (timing): The time dedicated to a given activity should be noted by project quarter (or, if the team prefers, by month). Budget: The budget can be provided by output or activity, and should be based off of the submitted and approved detailed budget. At the end of the year, budget spent v. activities planned and achieved can be assessed to show variance and alignment in spending and implementation. Budget variances of 5% or more at the total component level (as approved in ProDoc) needs to be approved by the WWF GEF Agency. Project Management Costs (PMC) cannot go over the total amount approved by GEF.
Tracking during Implementation In the AWP&B, progress can be tracked at the end of each project year under the columns labeled “Work Plan Tracking (Column M-P).” In the Results Framework, please track progress against targets in columns "actual" and "% achieved" for each year reported. Note that formulas will need to be adjusted if columns or rows have been added to this template. IP Rating: The project Implementation Progress (IP) rating is determined by averaging the achievement of all activities together in the workplan, rather than taking the average of component averages. Note that even if the project has exceeded an intended target associated with an activity (>100%), the rating will have to be manually adjusted to 100% to not skew the average. If there is a gender target in addition to a total target, both will contribute equally to the level of acheivement. DO Rating: The project Development Objective (DO) rating is determined by averaging the percent achievement of all indicators in the RF. Please note that some indicators have multiple measurements per indicator (e.g. 1 platform established with 200 registered users and 100 KM products) and it is recommended to average the achievement of all measurements taken per indicator (E.g. 1 platform, 100 users and 20 KM products would be 100% + 50% + 20% = 56%). The same would apply for a gender target. The snapshot tab will show a summary of progress again the AWP&B and RF over the life of the project.
Full Project Workplan The annual workplan activities and targets should align with the full project workplan, so please ensure that targets are cumulative through the end of the project and that the full suite of activities are represented. The template may need to be adjusted.
Additional Notes This completed spreadsheet will be submitted for approval of the AWP&B for planning purposes. Once the tracking aspects of the AWP&B and RF are completed, it will also be submitted and annexed to the annual Project Progress Report for reporting purposes. This template was designed for six years and five components, but please adjust this template to fit the realities of this project by inserting additional rows or columns. Please note that there are forumulas already input into the template that will need to be adjusted if you do add rows or columns. The password is GEF to unlock the sheet to input the formulas.

## Snapshot
Project: GEF-7 Cameroon CB IP
SNAPSHOT
Annual Work Plan Activity Tracking: Summary | [6 empty] | Results Framework Tracking: Summary
| % achievement | [5 empty] | Year | % average achievement
Component | Y1 | Y2 | Y3 | Y4 | Y5 | Y6
Component 1 | [6 empty] | Y1 | 0%
Component 2 |  | 0% |  |  |  |  | Y2 | 0%
Component 3 | [6 empty] | Y3 | 0%
Component 4 | [6 empty] | Y4 | 0%
Component 5 | [6 empty] | Y5 | 0%
PMC | 0% | 0% | 0% | 0% | 0% | 0% | Y6 | 0%
Average Activities |  | 0%
Average including management | 0% | 0% | 0% | 0% | 0% | 0%

## Results Framework
RESULTS MEASUREMENT FRAMEWORK
OUTCOME | INDICATOR | DEFINITION | METHOD | WHO | DISSAGREGATION | BASELINE | YR1 (July 1, 2022 -June 30, 2023) |  |  | YR2 (July 1, 2023 - June 30, 2024) |  |  | YR3 (2024-2025) |  |  | YR4 (2025-2026 |  |  | YR5 (2026-2027) |  |  | YR6 (Project end) |  |  | Assumption | NOTES
[7 empty] | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved
Project Objective: [fill in]
Global Environmental Benefits | Core Indicator 1: Terrestrial protected areas created or under improved management for conservation and sustainable use (hectares) | Number of hectares of protected area whose management has been improved. Cumulative | Assessed using METT, METT reports | PMU, conservation services | METT score by protected area
| GEF Sub-Indicator 1.2. Terrestial PA under improved management effectiveness |  |  |  |  | METT LNP (2020): 66 | METT |  |  | METT |  |  | METT |  |  | METT |  |  | METT
| Core Indicator 4: Area of landscapes under improved practices (hectares; excluding protected areas) | Cumulative | Calculated using GIS; Land use and management plans; Monitoring reports; Field reports | PMU executing partners | Sub-indicators 4.1 & 4.3 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Sub-indicator 4.1: Area of landscapes under improved management to benefit biodiversity | This indicator captures the landscape area being managed to benefit biodiversity, but which is not certified. |  |  |  | 0 | 0
| Sub-indicator 4.3: Area of landscapes under sustainable land management in production systems | This indicator captures the landscape area that is in production (e.g., agriculture, rangeland, and forests) and whose soil, air, and water are managed in a sustainable manner |  |  |  | 0
| Core Indicator 6: Greenhouse gas emission mitigated Sub-indicator 6.1: Carbon sequestered, or emissions avoided in the AFOLU sector | Carbon sequestration is defined as the process of increasing the carbon content of a reservoir/pool other than the atmosphere (IPCC, 2012). Avoided emissions refers to reduced emissions due to avoided deforestation or forest degradation, sustainable forest management, and improved practices on other land uses such as in agriculture. | t/ha/yr calculated using FAO EX-ACT Tool | PMU, executing partners | n/a | 0 t/ha/yr (Emissions without the project would be 4.8 t/ha/yr and with the project )
| GEF Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | Cumulative Direct beneficiary: individual who receives targeted support from a given GEF project and/or who uses specific resources that the project maintains or enhances. The beneficiary has to be aware that they are receiving this support or that they are using these specific resources. See GEF CORE Indicator guidelines for further guidance. | Field reports Training reports | PMU, executing partners | Women | 0
[5 empty] | Men | 0
[5 empty] | Total | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Project Objective achievement:
COMPONENT 1: [fill in]
Outcome 1.1: [fill in] |  | Non-cumulative |  | PMU, executing partners
|  | Non-cumulative |  | PMU
Component 1 achievement:
COMPONENT 2: [fill in]
Outcome 2.1: [fill in]
Outcome 2.2: [fill in] |  |  |  | PMU, executing partners
Outcome 2.3:[fill in] |  |  | Tracking by PMU and executing partners Monitoring reports
Component 2 achievement:
COMPONENT 3: [fill in]
Outcome 3.1: [fill in] |  |  |  | Executing partners | Women | 0 | 0 |  |  | 0
[5 empty] | Men | 0 | 0 |  |  | 0
[5 empty] | Youth | 0 | 0 |  |  | 0
[5 empty] | Total | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
Outcome 3.2: [fill in] |  |  |  | Executing partners | Women | 0 | 0 |  |  | 0
[5 empty] | Men | 0 | 0 |  |  | 0
[5 empty] | Youth | 0 | 0 |  |  | 0
[5 empty] | Total | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
Component 3 achievement:
COMPONENT 4:[fill in]
Outcome 4.1: [fill in]
Women
Men
Youth
[5 empty] | Total | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
Component 4 achievement:
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination
Outcome 5.1: [fill in] | # of M&E plan implemented | Implemented: refers to completion of project progress reports (PPR) and Project Closeout Report (PCR), quarterly financial reports (QFR), reflection exercise (RE) completed with Results Framework and ToC assessed and validated or modified, and midterm and terminal evaluations (MTE and TE) completed. | Tracking of development and implementation of M&E Plan by PMU | PMU | n/a
| # of communications, awareness raising, and KM materials produced and proportion (%) that target women (and other vulnerable groups) | Cumulative Type (e.g., radio program, television, program, technical brief, case study, articles) Target group, as applicable (e.g., women, youth, indigenous peoples) Subject area | Tracking by PMU Communication & Knowledge Management Strategy Communic-ation & KM materials | PMU | #
% that target women and other vulnerable groups
| # of bilateral or regional events to coordinate and exchange knowledge on project strategies for transboundary landscapes in which Cameroon is represented as a result of this project | Cumulative | Tracking by PMU Participation logs | PMU | Type (e.g., bilateral, landscape, regional) Subject area | 0 | 1 |  | 0% | 3 |  | 0% | 5 |  | 0% | 7 |  | 0% | 9 |  | 0% | 10 |  | 0%
Component 5 achievement: | [8 empty] | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
[6 empty] | Total % achieved |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%

## Full Project Workplan
FULL PROJECT WORKPLAN
Component | Outcome | Output | Activity # | Activities | Who | Timeline (Y1, Y2, Y3, etc.) | Budget (at activity, output, or outcome level)

## AWPB Yr 1
Period: Year 1 (month, Day, year - month,Day, year)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | in local currency | in USD | if activity is carried over from previous year | # of | [5 empty] | in CFA Franc (FCFA) | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Component 1: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 1.1 |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 1.1.1. | 1 | Activity 1.1.1.1: | [6 empty] | 0
| 2 | 1.1.1.2: | [6 empty] | 0
| 3 | 1.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.1.2 | 4 | 1.1.2.1: | [6 empty] | 0
| 5 | 1.1.2.2: | [6 empty] | 0
| 6 | 1.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Component 2: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 2.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 | 7 | 2.1.1.1: | [6 empty] | 0
| 8 | 2.1.1.2: | [6 empty] | 0
| 9 | 2.1.1.3: | [6 empty] | 0
| 10 | 2.1.1.4: | [6 empty] | 0
| 11 | 2.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 2.1.2: | 12 | 2.1.2.1: | [6 empty] | 0
| 13 | 2.1.2.2: | [6 empty] | 0
| 14 | 2.1.2.3: | [6 empty] | 0
| 15 | 2.1.2.4: | [6 empty] | 0
| 16 | 2.1.2.5: | [6 empty] | 0
| 17 | 2.1.2.6: | [6 empty] | 0
| 18 | 2.1.2.7: | [6 empty] | 0
| 19 | 2.1.2.8: | [6 empty] | 0
| 20 | 2.1.2.10: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.2.1: | 21 | 2.2.1.1: | [6 empty] | 0
| 22 | 2.2.1.2: | [6 empty] | 0
| 23 | 2.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.3: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.3.1: | 24 | 2.3.1.1: | [6 empty] | 0
| 25 | 2.3.1.2: | [6 empty] | 0
| 26 | 2.3.1.3: | [6 empty] | 0
| 27 | 2.3.1.4: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 3: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 3.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.1.1: | 28 | 3.1.1.1: | [6 empty] | 0
| 29 | 3.1.1.2: | [6 empty] | 0
| 30 | 3.1.1.3 | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.1.2: | 31 | 3.1.2.1: | [6 empty] | 0
| 32 | 3.1.2.2: | [6 empty] | 0
| 33 | 3.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.2.1: | 34 | 3.2.1.1: | [6 empty] | 0
| 35 | 3.2.1.2: | [6 empty] | 0
| 36 | 3.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: | 37 | 3.2.2.1: | [6 empty] | 0
| 38 | 3.2.2.2: | [6 empty] | 0
| 39 | 3.2.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 4: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 4.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 4.1.1: | 40 | 4.1.1.1: | [6 empty] | 0
| 41 | 4.1.1.2: | [6 empty] | 0
| 42 | 4.1.1.3: | [6 empty] | 0
| 43 | 4.1.1.4: | [6 empty] | 0
| 44 | 4.1.1.5: | [6 empty] | 0
| 45 | 4.1.1.6: | [6 empty] | 0
| 46 | 4.1.1.7: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.2: | 47 | 4.1.2.1: | [6 empty] | 0
| 48 | 4.1.2.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.3: | 49 | 4.1.3.1: | [6 empty] | 0
| 50 | 4.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 5.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 5.1.1: Effective project coordination and gender-sensitive monitoring evaluation | 51 | 5.1.1.1: Establish Steering Committee, PMU and hold inception workshop | [6 empty] | 0
| 52 | 5.1.1.2: Develop and implement a project-level results-based Monitoring & Evaluation Plan, including monitoring implementation of Gender Action Plan, Stakeholder Engagement Plan and Social and Environmental Management Plan | [6 empty] | 0
| 53 | 5.1.1.4: Lead project coordination, including adaptive project planning and management, and quarterly and annual reporting | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.2: Project achievements and results documented and knowledge management products prepared for replication and scaling up | 54 | 5.1.2.1: Develop project communication and knowledge management strategy | [6 empty] | 0
| 55 | 5.1.2.2: Design materials to communicate project results and lessons learned, including conditions and recommendations for replication and scaling up, | [6 empty] | 0
| 56 | 5.1.2.3: Share project results and lessons learned through sub-national, national, regional, and international knowledge management platforms | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.3: | 57 | 5.1.3.1: | [6 empty] | 0
| 58 | 5.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
B. Project Management Costs | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 59 | Steering Committee Meetings | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 60 | Annual Reflection Meetings and Preparation of Workplan/Budget | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 61 | Synchronization of Activities in the context of Project Implementation | PMU | [5 empty] | 0
| 62 | executing agency support to Supervision missions | PMU | [5 empty] | 0 |  | site visits+meetings | 1 |  | 0%
| 63 | Other direct cost | PMU | [5 empty] | 0
| 64 | PMU Personnel cost for project management (others under activities in the componensts) | PMU | [5 empty] | 0
[8 empty] | 0 | 0 |  |  | 3 | 0 | 0% | 0% | 0% | 0 | 0
|  | Capital Assets | [6 empty] | 0
| 65 | IT equipment for PMU | PMU
| 66 |  | PMU
| 67 |  | PMU | [7 empty] | # IT equipment (GIS LAB) package (1) # Supplies (software package) (1) # Supplies (office-package) (6) # Internet access - (6 months) # Office (maintenance package) (1) | 15
GRAND TOTAL (A+B) |  |  |  | YR 1 |  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [11 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year |  |  |  |  | 0 | 0

## AWPB Yr 2
Period: Year 2 (month, Day, year - month,Day, year)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | in local currency | in USD | if activity is carried over from previous year | # of | [5 empty] | in CFA Franc (FCFA) | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Component 1: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 1.1 |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 1.1.1. | 68 | Activity 1.1.1.1: | [6 empty] | 0
| 69 | 1.1.1.2: | [6 empty] | 0
| 70 | 1.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.1.2 | 71 | 1.1.2.1: | [6 empty] | 0
| 72 | 1.1.2.2: | [6 empty] | 0
| 73 | 1.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Component 2: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 2.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 | 74 | 2.1.1.1: | [6 empty] | 0
| 75 | 2.1.1.2: | [6 empty] | 0
| 76 | 2.1.1.3: | [6 empty] | 0
| 77 | 2.1.1.4: | [6 empty] | 0
| 78 | 2.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 2.1.2: | 79 | 2.1.2.1: | [6 empty] | 0
| 80 | 2.1.2.2: | [6 empty] | 0
| 81 | 2.1.2.3: | [6 empty] | 0
| 82 | 2.1.2.4: | [6 empty] | 0
| 83 | 2.1.2.5: | [6 empty] | 0
| 84 | 2.1.2.6: | [6 empty] | 0
| 85 | 2.1.2.7: | [6 empty] | 0
| 86 | 2.1.2.8: | [6 empty] | 0
| 87 | 2.1.2.10: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.2.1: | 88 | 2.2.1.1: | [6 empty] | 0
| 89 | 2.2.1.2: | [6 empty] | 0
| 90 | 2.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.3: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.3.1: | 91 | 2.3.1.1: | [6 empty] | 0
| 92 | 2.3.1.2: | [6 empty] | 0
| 93 | 2.3.1.3: | [6 empty] | 0 |  |  | 10 |  | 0%
| 94 | 2.3.1.4: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 10 | 0 | 0% | 0% | 0% | 0 | 0
COMPONENT 3: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 3.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.1.1: | 95 | 3.1.1.1: | [6 empty] | 0
| 96 | 3.1.1.2: | [6 empty] | 0
| 97 | 3.1.1.3 | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.1.2: | 98 | 3.1.2.1: | [6 empty] | 0
| 99 | 3.1.2.2: | [6 empty] | 0
| 100 | 3.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.2.1: | 101 | 3.2.1.1: | [6 empty] | 0
| 102 | 3.2.1.2: | [6 empty] | 0
| 103 | 3.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: | 104 | 3.2.2.1: | [6 empty] | 0
| 105 | 3.2.2.2: | [6 empty] | 0
| 106 | 3.2.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 4: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 4.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 4.1.1: | 107 | 4.1.1.1: | [6 empty] | 0
| 108 | 4.1.1.2: | [6 empty] | 0
| 109 | 4.1.1.3: | [6 empty] | 0
| 110 | 4.1.1.4: | [6 empty] | 0
| 111 | 4.1.1.5: | [6 empty] | 0
| 112 | 4.1.1.6: | [6 empty] | 0
| 113 | 4.1.1.7: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.2: | 114 | 4.1.2.1: | [6 empty] | 0
| 115 | 4.1.2.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.3: | 116 | 4.1.3.1: | [6 empty] | 0
| 117 | 4.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 5.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 5.1.1: Effective project coordination and gender-sensitive monitoring evaluation | 118 | 5.1.1.1: Establish Steering Committee, PMU and hold inception workshop | [6 empty] | 0
| 119 | 5.1.1.2: Develop and implement a project-level results-based Monitoring & Evaluation Plan, including monitoring implementation of Gender Action Plan, Stakeholder Engagement Plan and Social and Environmental Management Plan | [6 empty] | 0
| 120 | 5.1.1.4: Lead project coordination, including adaptive project planning and management, and quarterly and annual reporting | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.2: Project achievements and results documented and knowledge management products prepared for replication and scaling up | 121 | 5.1.2.1: Develop project communication and knowledge management strategy | [6 empty] | 0
| 122 | 5.1.2.2: Design materials to communicate project results and lessons learned, including | [6 empty] | 0
| 123 | 5.1.2.3: Share project results and lessons learned through sub-national, national, regional, and international knowledge management platforms | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.3: | 124 | 5.1.3.1: | [6 empty] | 0
| 125 | 5.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
B. Project Management Costs | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 126 | Steering Committee Meetings | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 127 | Annual Reflection Meetings and Preparation of Workplan/Budget | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 128 | Synchronization of Activities in the context of Project Implementation | PMU | [5 empty] | 0
| 129 | executing agency support to Supervision missions | PMU | [5 empty] | 0 |  | site visits+meetings | 1 |  | 0%
| 130 | Other direct cost | PMU | [5 empty] | 0
| 131 | PMU Personnel cost for project management (others under activities in the componensts) | PMU | [5 empty] | 0
[8 empty] | 0 | 0 |  |  | 3 | 0 | 0% | 0% | 0% | 0 | 0
|  | Capital Assets | [6 empty] | 0
| 132 | IT equipment for PMU | PMU
| 133 |  | PMU
| 134 |  | PMU | [7 empty] | # IT equipment (GIS LAB) package (1) # Supplies (software package) (1) # Supplies (office-package) (6) # Internet access - (6 months) # Office (maintenance package) (1) | 15
GRAND TOTAL (A+B) |  |  |  | YR 2 |  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [11 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year |  |  |  |  | 0 | 0

## AWPB Yr 3
Period: Year 3 (month, Day, year - month,Day, year)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | in local currency | in USD | if activity is carried over from previous year | # of | [5 empty] | in CFA Franc (FCFA) | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Component 1: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 1.1 |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 1.1.1. | 135 | Activity 1.1.1.1: | [6 empty] | 0
| 136 | 1.1.1.2: | [6 empty] | 0
| 137 | 1.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.1.2 | 138 | 1.1.2.1: | [6 empty] | 0
| 139 | 1.1.2.2: | [6 empty] | 0
| 140 | 1.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Component 2: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 2.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 | 141 | 2.1.1.1: | [6 empty] | 0
| 142 | 2.1.1.2: | [6 empty] | 0
| 143 | 2.1.1.3: | [6 empty] | 0
| 144 | 2.1.1.4: | [6 empty] | 0
| 145 | 2.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 2.1.2: | 146 | 2.1.2.1: | [6 empty] | 0
| 147 | 2.1.2.2: | [6 empty] | 0
| 148 | 2.1.2.3: | [6 empty] | 0
| 149 | 2.1.2.4: | [6 empty] | 0
| 150 | 2.1.2.5: | [6 empty] | 0
| 151 | 2.1.2.6: | [6 empty] | 0
| 152 | 2.1.2.7: | [6 empty] | 0
| 153 | 2.1.2.8: | [6 empty] | 0
| 154 | 2.1.2.10: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.2.1: | 155 | 2.2.1.1: | [6 empty] | 0
| 156 | 2.2.1.2: | [6 empty] | 0
| 157 | 2.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.3: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.3.1: | 158 | 2.3.1.1: | [6 empty] | 0
| 159 | 2.3.1.2: | [6 empty] | 0
| 160 | 2.3.1.3: | [6 empty] | 0
| 161 | 2.3.1.4: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 3: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 3.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.1.1: | 162 | 3.1.1.1: | [6 empty] | 0
| 163 | 3.1.1.2: | [6 empty] | 0
| 164 | 3.1.1.3 | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.1.2: | 165 | 3.1.2.1: | [6 empty] | 0
| 166 | 3.1.2.2: | [6 empty] | 0
| 167 | 3.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.2.1: | 168 | 3.2.1.1: | [6 empty] | 0
| 169 | 3.2.1.2: | [6 empty] | 0
| 170 | 3.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: | 171 | 3.2.2.1: | [6 empty] | 0
| 172 | 3.2.2.2: | [6 empty] | 0
| 173 | 3.2.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 4: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 4.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 4.1.1: | 174 | 4.1.1.1: | [6 empty] | 0
| 175 | 4.1.1.2: | [6 empty] | 0
| 176 | 4.1.1.3: | [6 empty] | 0
| 177 | 4.1.1.4: | [6 empty] | 0
| 178 | 4.1.1.5: | [6 empty] | 0
| 179 | 4.1.1.6: | [6 empty] | 0
| 180 | 4.1.1.7: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.2: | 181 | 4.1.2.1: | [6 empty] | 0
| 182 | 4.1.2.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.3: | 183 | 4.1.3.1: | [6 empty] | 0
| 184 | 4.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 5.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 5.1.1: Effective project coordination and gender-sensitive monitoring evaluation | 185 | 5.1.1.1: Establish Steering Committee, PMU and hold inception workshop | [6 empty] | 0
| 186 | 5.1.1.2: Develop and implement a project-level results-based Monitoring & Evaluation Plan, including monitoring implementation of Gender Action Plan, Stakeholder Engagement Plan and Social and Environmental Management Plan | [6 empty] | 0
| 187 | 5.1.1.4: Lead project coordination, including adaptive project planning and management, and quarterly and annual reporting | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.2: Project achievements and results documented and knowledge management products prepared for replication and scaling up | 188 | 5.1.2.1: Develop project communication and knowledge management strategy | [6 empty] | 0
| 189 | 5.1.2.2: Design materials to communicate project results and lessons learned, including | [6 empty] | 0
| 190 | 5.1.2.3: Share project results and lessons learned through sub-national, national, regional, and international knowledge management platforms | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.3: | 191 | 5.1.3.1: | [6 empty] | 0
| 192 | 5.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
B. Project Management Costs | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 193 | Steering Committee Meetings | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 194 | Annual Reflection Meetings and Preparation of Workplan/Budget | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 195 | Synchronization of Activities in the context of Project Implementation | PMU | [5 empty] | 0
| 196 | executing agency support to Supervision missions | PMU | [5 empty] | 0 |  | site visits+meetings | 1 |  | 0%
| 197 | Other direct cost | PMU | [5 empty] | 0
| 198 | PMU Personnel cost for project management (others under activities in the componensts) | PMU | [5 empty] | 0
[8 empty] | 0 | 0 |  |  | 3 | 0 | 0% | 0% | 0% | 0 | 0
|  | Capital Assets | [6 empty] | 0
| 199 | IT equipment for PMU | PMU
| 200 |  | PMU
| 201 |  | PMU | [7 empty] | # IT equipment (GIS LAB) package (1) # Supplies (software package) (1) # Supplies (office-package) (6) # Internet access - (6 months) # Office (maintenance package) (1) | 15
GRAND TOTAL (A+B) |  |  |  | YR 3 |  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [11 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year |  |  |  |  | 0 | 0

## AWPB Yr 4
Period: Year 4 (month, Day, year - month,Day, year)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | in local currency | in USD | if activity is carried over from previous year | # of | [5 empty] | in CFA Franc (FCFA) | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Component 1: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 1.1 |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 1.1.1. | 202 | Activity 1.1.1.1: | [6 empty] | 0
| 203 | 1.1.1.2: | [6 empty] | 0
| 204 | 1.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.1.2 | 205 | 1.1.2.1: | [6 empty] | 0
| 206 | 1.1.2.2: | [6 empty] | 0
| 207 | 1.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Component 2: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 2.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 | 208 | 2.1.1.1: | [6 empty] | 0
| 209 | 2.1.1.2: | [6 empty] | 0
| 210 | 2.1.1.3: | [6 empty] | 0
| 211 | 2.1.1.4: | [6 empty] | 0
| 212 | 2.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 2.1.2: | 213 | 2.1.2.1: | [6 empty] | 0
| 214 | 2.1.2.2: | [6 empty] | 0
| 215 | 2.1.2.3: | [6 empty] | 0
| 216 | 2.1.2.4: | [6 empty] | 0
| 217 | 2.1.2.5: | [6 empty] | 0
| 218 | 2.1.2.6: | [6 empty] | 0
| 219 | 2.1.2.7: | [6 empty] | 0
| 220 | 2.1.2.8: | [6 empty] | 0
| 221 | 2.1.2.10: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.2.1: | 222 | 2.2.1.1: | [6 empty] | 0
| 223 | 2.2.1.2: | [6 empty] | 0
| 224 | 2.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.3: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.3.1: | 225 | 2.3.1.1: | [6 empty] | 0
| 226 | 2.3.1.2: | [6 empty] | 0
| 227 | 2.3.1.3: | [6 empty] | 0
| 228 | 2.3.1.4: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 3: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 3.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.1.1: | 229 | 3.1.1.1: | [6 empty] | 0
| 230 | 3.1.1.2: | [6 empty] | 0
| 231 | 3.1.1.3 | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.1.2: | 232 | 3.1.2.1: | [6 empty] | 0
| 233 | 3.1.2.2: | [6 empty] | 0
| 234 | 3.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.2.1: | 235 | 3.2.1.1: | [6 empty] | 0
| 236 | 3.2.1.2: | [6 empty] | 0
| 237 | 3.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: | 238 | 3.2.2.1: | [6 empty] | 0
| 239 | 3.2.2.2: | [6 empty] | 0
| 240 | 3.2.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 4: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 4.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 4.1.1: | 241 | 4.1.1.1: | [6 empty] | 0
| 242 | 4.1.1.2: | [6 empty] | 0
| 243 | 4.1.1.3: | [6 empty] | 0
| 244 | 4.1.1.4: | [6 empty] | 0
| 245 | 4.1.1.5: | [6 empty] | 0
| 246 | 4.1.1.6: | [6 empty] | 0
| 247 | 4.1.1.7: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.2: | 248 | 4.1.2.1: | [6 empty] | 0
| 249 | 4.1.2.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.3: | 250 | 4.1.3.1: | [6 empty] | 0
| 251 | 4.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 5.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 5.1.1: Effective project coordination and gender-sensitive monitoring evaluation | 252 | 5.1.1.1: Establish Steering Committee, PMU and hold inception workshop | [6 empty] | 0
| 253 | 5.1.1.2: Develop and implement a project-level results-based Monitoring & Evaluation Plan, including monitoring implementation of Gender Action Plan, Stakeholder Engagement Plan and Social and Environmental Management Plan | [6 empty] | 0
| 254 | 5.1.1.4: Lead project coordination, including adaptive project planning and management, and quarterly and annual reporting | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.2: Project achievements and results documented and knowledge management products prepared for replication and scaling up | 255 | 5.1.2.1: Develop project communication and knowledge management strategy | [6 empty] | 0
| 256 | 5.1.2.2: Design materials to communicate project results and lessons learned, including | [6 empty] | 0
| 257 | 5.1.2.3: Share project results and lessons learned through sub-national, national, regional, and international knowledge management platforms | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.3: | 258 | 5.1.3.1: | [6 empty] | 0
| 259 | 5.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
B. Project Management Costs | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 260 | Steering Committee Meetings | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 261 | Annual Reflection Meetings and Preparation of Workplan/Budget | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 262 | Synchronization of Activities in the context of Project Implementation | PMU | [5 empty] | 0
| 263 | executing agency support to Supervision missions | PMU | [5 empty] | 0 |  | site visits+meetings | 1 |  | 0%
| 264 | Other direct cost | PMU | [5 empty] | 0
| 265 | PMU Personnel cost for project management (others under activities in the componensts) | PMU | [5 empty] | 0
[8 empty] | 0 | 0 |  |  | 3 | 0 | 0% | 0% | 0% | 0 | 0
|  | Capital Assets | [6 empty] | 0
| 266 | IT equipment for PMU | PMU
| 267 |  | PMU
| 268 |  | PMU | [7 empty] | # IT equipment (GIS LAB) package (1) # Supplies (software package) (1) # Supplies (office-package) (6) # Internet access - (6 months) # Office (maintenance package) (1) | 15
GRAND TOTAL (A+B) |  |  |  | YR 4 |  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [11 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year |  |  |  |  | 0 | 0

## AWPB Yr 5
Period: Year 5 (month, Day, year - month,Day, year)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | in local currency | in USD | if activity is carried over from previous year | # of | [5 empty] | in CFA Franc (FCFA) | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Component 1: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 1.1 |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 1.1.1. | 269 | Activity 1.1.1.1: | [6 empty] | 0
| 270 | 1.1.1.2: | [6 empty] | 0
| 271 | 1.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.1.2 | 272 | 1.1.2.1: | [6 empty] | 0
| 273 | 1.1.2.2: | [6 empty] | 0
| 274 | 1.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Component 2: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 2.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 | 275 | 2.1.1.1: | [6 empty] | 0
| 276 | 2.1.1.2: | [6 empty] | 0
| 277 | 2.1.1.3: | [6 empty] | 0
| 278 | 2.1.1.4: | [6 empty] | 0
| 279 | 2.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 2.1.2: | 280 | 2.1.2.1: | [6 empty] | 0
| 281 | 2.1.2.2: | [6 empty] | 0
| 282 | 2.1.2.3: | [6 empty] | 0
| 283 | 2.1.2.4: | [6 empty] | 0
| 284 | 2.1.2.5: | [6 empty] | 0
| 285 | 2.1.2.6: | [6 empty] | 0
| 286 | 2.1.2.7: | [6 empty] | 0
| 287 | 2.1.2.8: | [6 empty] | 0
| 288 | 2.1.2.10: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.2.1: | 289 | 2.2.1.1: | [6 empty] | 0
| 290 | 2.2.1.2: | [6 empty] | 0
| 291 | 2.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.3: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.3.1: | 292 | 2.3.1.1: | [6 empty] | 0
| 293 | 2.3.1.2: | [6 empty] | 0
| 294 | 2.3.1.3: | [6 empty] | 0
| 295 | 2.3.1.4: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 3: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 3.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.1.1: | 296 | 3.1.1.1: | [6 empty] | 0
| 297 | 3.1.1.2: | [6 empty] | 0
| 298 | 3.1.1.3 | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.1.2: | 299 | 3.1.2.1: | [6 empty] | 0
| 300 | 3.1.2.2: | [6 empty] | 0
| 301 | 3.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.2.1: | 302 | 3.2.1.1: | [6 empty] | 0
| 303 | 3.2.1.2: | [6 empty] | 0
| 304 | 3.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: | 305 | 3.2.2.1: | [6 empty] | 0
| 306 | 3.2.2.2: | [6 empty] | 0
| 307 | 3.2.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 4: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 4.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 4.1.1: | 308 | 4.1.1.1: | [6 empty] | 0
| 309 | 4.1.1.2: | [6 empty] | 0
| 310 | 4.1.1.3: | [6 empty] | 0
| 311 | 4.1.1.4: | [6 empty] | 0
| 312 | 4.1.1.5: | [6 empty] | 0
| 313 | 4.1.1.6: | [6 empty] | 0
| 314 | 4.1.1.7: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.2: | 315 | 4.1.2.1: | [6 empty] | 0
| 316 | 4.1.2.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.3: | 317 | 4.1.3.1: | [6 empty] | 0
| 318 | 4.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 5.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 5.1.1: Effective project coordination and gender-sensitive monitoring evaluation | 319 | 5.1.1.1: Establish Steering Committee, PMU and hold inception workshop | [6 empty] | 0
| 320 | 5.1.1.2: Develop and implement a project-level results-based Monitoring & Evaluation Plan, including monitoring implementation of Gender Action Plan, Stakeholder Engagement Plan and Social and Environmental Management Plan | [6 empty] | 0
| 321 | 5.1.1.4: Lead project coordination, including adaptive project planning and management, and quarterly and annual reporting | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.2: Project achievements and results documented and knowledge management products prepared for replication and scaling up | 322 | 5.1.2.1: Develop project communication and knowledge management strategy | [6 empty] | 0
| 323 | 5.1.2.2: Design materials to communicate project results and lessons learned, including | [6 empty] | 0
| 324 | 5.1.2.3: Share project results and lessons learned through sub-national, national, regional, and international knowledge management platforms | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.3: | 325 | 5.1.3.1: | [6 empty] | 0
| 326 | 5.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
B. Project Management Costs | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 327 | Steering Committee Meetings | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 328 | Annual Reflection Meetings and Preparation of Workplan/Budget | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 329 | Synchronization of Activities in the context of Project Implementation | PMU | [5 empty] | 0
| 330 | executing agency support to Supervision missions | PMU | [5 empty] | 0 |  | site visits+meetings | 1 |  | 0%
| 331 | Other direct cost | PMU | [5 empty] | 0
| 332 | PMU Personnel cost for project management (others under activities in the componensts) | PMU | [5 empty] | 0
[8 empty] | 0 | 0 |  |  | 3 | 0 | 0% | 0% | 0% | 0 | 0
|  | Capital Assets | [6 empty] | 0
| 333 | IT equipment for PMU | PMU
| 334 |  | PMU
| 335 |  | PMU | [7 empty] | # IT equipment (GIS LAB) package (1) # Supplies (software package) (1) # Supplies (office-package) (6) # Internet access - (6 months) # Office (maintenance package) (1) | 15
GRAND TOTAL (A+B) |  |  |  | YR 5 |  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [11 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year |  |  |  |  | 0 | 0

## AWPB Yr 6
Period: Year 6 (month, Day, year - month,Day, year)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | in local currency | in USD | if activity is carried over from previous year | # of | [5 empty] | in CFA Franc (FCFA) | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Component 1: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 1.1 |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 1.1.1. | 336 | Activity 1.1.1.1: | [6 empty] | 0
| 337 | 1.1.1.2: | [6 empty] | 0
| 338 | 1.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.1.2 | 339 | 1.1.2.1: | [6 empty] | 0
| 340 | 1.1.2.2: | [6 empty] | 0
| 341 | 1.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Component 2: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 2.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 | 342 | 2.1.1.1: | [6 empty] | 0
| 343 | 2.1.1.2: | [6 empty] | 0
| 344 | 2.1.1.3: | [6 empty] | 0
| 345 | 2.1.1.4: | [6 empty] | 0
| 346 | 2.1.1.5: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 2.1.2: | 347 | 2.1.2.1: | [6 empty] | 0
| 348 | 2.1.2.2: | [6 empty] | 0
| 349 | 2.1.2.3: | [6 empty] | 0
| 350 | 2.1.2.4: | [6 empty] | 0
| 351 | 2.1.2.5: | [6 empty] | 0
| 352 | 2.1.2.6: | [6 empty] | 0
| 353 | 2.1.2.7: | [6 empty] | 0
| 354 | 2.1.2.8: | [6 empty] | 0
| 355 | 2.1.2.10: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.2.1: | 356 | 2.2.1.1: | [6 empty] | 0
| 357 | 2.2.1.2: | [6 empty] | 0
| 358 | 2.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.3: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 2.3.1: | 359 | 2.3.1.1: | [6 empty] | 0
| 360 | 2.3.1.2: | [6 empty] | 0
| 361 | 2.3.1.3: | [6 empty] | 0
| 362 | 2.3.1.4: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 3: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 3.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.1.1: | 363 | 3.1.1.1: | [6 empty] | 0
| 364 | 3.1.1.2: | [6 empty] | 0
| 365 | 3.1.1.3 | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.1.2: | 366 | 3.1.2.1: | [6 empty] | 0
| 367 | 3.1.2.2: | [6 empty] | 0
| 368 | 3.1.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.2: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 3.2.1: | 369 | 3.2.1.1: | [6 empty] | 0
| 370 | 3.2.1.2: | [6 empty] | 0
| 371 | 3.2.1.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: | 372 | 3.2.2.1: | [6 empty] | 0
| 373 | 3.2.2.2: | [6 empty] | 0
| 374 | 3.2.2.3: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 4: | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 4.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 4.1.1: | 375 | 4.1.1.1: | [6 empty] | 0
| 376 | 4.1.1.2: | [6 empty] | 0
| 377 | 4.1.1.3: | [6 empty] | 0
| 378 | 4.1.1.4: | [6 empty] | 0
| 379 | 4.1.1.5: | [6 empty] | 0
| 380 | 4.1.1.6: | [6 empty] | 0
| 381 | 4.1.1.7: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.2: | 382 | 4.1.2.1: | [6 empty] | 0
| 383 | 4.1.2.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 4.1.3: | 384 | 4.1.3.1: | [6 empty] | 0
| 385 | 4.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 5: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Outcome 5.1: |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Output 5.1.1: Effective project coordination and gender-sensitive monitoring evaluation | 386 | 5.1.1.1: Establish Steering Committee, PMU and hold inception workshop | [6 empty] | 0
| 387 | 5.1.1.2: Develop and implement a project-level results-based Monitoring & Evaluation Plan, including monitoring implementation of Gender Action Plan, SEP and Social and Environmental Management Plan | [6 empty] | 0
| 388 | 5.1.1.4: Lead project coordination, including adaptive project planning and management, and quarterly and annual reporting | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.2: Project achievements and results documented and knowledge management products prepared for replication and scaling up | 389 | 5.1.2.1: Develop project communication and knowledge management strategy | [6 empty] | 0
| 390 | 5.1.2.2: Design materials to communicate project results and lessons learned, including | [6 empty] | 0
| 391 | 5.1.2.3: Share project results and lessons learned through sub-national, national, regional, and international knowledge management platforms | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 5.1.3: | 392 | 5.1.3.1: | [6 empty] | 0
| 393 | 5.1.3.2: | [6 empty] | 0
[8 empty] | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
B. Project Management Costs | [7 empty] | 0 | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 394 | Steering Committee Meetings | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 395 | Annual Reflection Meetings and Preparation of Workplan/Budget | PMU | [5 empty] | 0 |  | meetings | 1 |  | 0%
| 396 | Synchronization of Activities in the context of Project Implementation | PMU | [5 empty] | 0
| 397 | executing agency support to Supervision missions | PMU | [5 empty] | 0 |  | site visits+meetings | 1 |  | 0%
| 398 | Other direct cost | PMU | [5 empty] | 0
| 399 | PMU Personnel cost for project management (others under activities in the componensts) | PMU | [5 empty] | 0
[8 empty] | 0 | 0 |  |  | 3 | 0 | 0% | 0% | 0% | 0 | 0
|  | Capital Assets | [6 empty] | 0
| 400 | IT equipment for PMU | PMU
| 401 |  | PMU
| 402 |  | PMU | [7 empty] | # IT equipment (GIS LAB) package (1) # Supplies (software package) (1) # Supplies (office-package) (6) # Internet access - (6 months) # Office (maintenance package) (1) | 15
GRAND TOTAL (A+B) |  |  |  | YR 6 |  |  |  | 0 | 0 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [11 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year |  |  |  |  | 0 | 0